## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Fitness module
| Table 1 | Fitness module

## Fitness module
FeedNow Mobile App (iOS + Android)
| Web Services Integration | Day | Cost in Dollar
Splash / Login : UI with Functionality | Yes | 5 | 5000
Seller List with all seller functionality integration : UI with Functionality Task | Yes | 20
Address functionality : UI with Functionality | Yes | 10 | 6000
About Us, Contact Us, Privacy Policy, Security Policy, Refund Policy and My Account : UI with Functionality | Yes | 10
Total days |  | 45 | 11000
FeedNow Driver Mobile App (iOS + Android)
Splash / Login : UI with Functionality | Yes | 5 | 2000
Seller List with all seller functionality integration : UI with Functionality Task | Yes | 10 | 1000
Address functionality : UI with Functionality | Yes | 10 | 2000
Interest screen |  | 2
About Us, Contact Us, Privacy Policy, Security Policy, Refund Policy and My Account : UI with Functionality | Yes | 10 | 1000
Total days |  | 35 | 6000
Interest screen |  | 2
Grand Total days |  | 80 | 17,000 /-